## Sheet1
Date | Number of Hours | Description of Work Done
2025-01-16 | 1 | Coming up with ideas for the project
2025-01-17 | 1 | In-class consultation about 2 different project ideas
2025-01-21 | 0.5 | Deciding the idea for the project
2025-01-23 | 1 | Starting the project proposal
2025-01-24 | 1 | In-class project consultation and inital check-in
2025-01-24 | 2 | Defining the project's scope and features after consultation
2025-01-25 | 3 | Continuing project proposal writing
2025-01-26 | 4 | Finishing project proposal and submitting
2025-02-07 | 2 | Coming up with the possible endpoints
2025-02-08 | 5 | Setting up the backend and writing the project report
2025-02-08 | 1 | Committing to github repo